## Task Table
EBECC Project Gantt
TASK INPUTS
Task | Owner | Deliverable | Start | End | Duration (days) | Progress
Colleges - Complete Competitive Capital Projects | Colleges | N | 2027-08-01 | 2028-02-28 | 212
Colleges - Create Energy Reduction Plan | Colleges | Y | 2027-01-01 | 2027-06-30 | 181
Colleges - Draft Energy Project Planning Team Narrative - IGA 1(a) | Colleges | N | 2026-08-01 | 2026-08-31 | 31 | 20%
Colleges - Input Energy Use Data into PM | Colleges | Y | 2026-06-01 | 2026-09-30 | 122
Colleges - Install Submeters | Colleges | Y | 2026-09-30 | 2026-12-31 | 93
Colleges - News Release through Social Media/Newspaper | Colleges | N | 2026-09-01 | 2026-12-31 | 122
Colleges - News Release through Social Media/Newspaper | Colleges | N | 2028-03-01 | 2028-03-31 | 31
Colleges - Select Energy Efficiency Capital Projects for Submitting NOFO | Colleges | N | 2027-01-01 | 2027-05-31 | 151 | 0%
Colleges - Submit Competitive Project Applications | Colleges | N | 2027-06-01 | 2027-07-01 | 31
Colleges - Submit Final Invoices | Colleges | Y | 2028-03-01 | 2028-03-08 | 8
ES - Develop Submetering Plans | EnergySense | Y | 2026-05-31 | 2026-09-30 | 123
ES - Draft Final Version of Energy Vision, Goals, and Strategies for Participating Colleges | EnergySense | Y | 2026-09-01 | 2028-03-31 | 578 | 0%
ES - Provide Technical Assistance for Energy Star Portfolio Manager - IGA 1(b) | EnergySense | Y | 2026-02-01 | 2026-09-30 | 242 | 100%
ES - Site Visit for Submetering Discussion | EnergySense | Y | 2026-04-01 | 2026-05-31 | 61 | 100%
ES - Work with Colleges for Evaluation of Capital Project Needs | EnergySense | N | 2027-01-01 | 2027-05-31 | 151
IGEN - Begin Recruiting Colleges | IGEN | Y | 2025-07-01 | 2026-03-31 | 274 | 100%
IGEN - Choose Competitive Projects to Award | IGEN | Y | 2027-07-01 | 2027-08-01 | 32
IGEN - Complete Program Overview Required in 1(f) of IGA | IGEN | Y | 2027-01-01 | 2028-04-30 | 486
IGEN - Final Reimbursement Request | IGEN | Y | 2028-06-01 | 2028-07-15 | 45 | 0%
IGEN - Submit Final Narrative Project Report | IGEN | Y | 2025-07-01 | 2028-07-01 | 1097 | 0%

## Energy Planning Teams
First Name | Last Name | Title | College/Organization | Email | Phone | Cell Phone | IGEN Rep | Liaison | College Role | Nov
James | Beckom | Vice President of Finance and Chief Financial Officer | College of Lake County | jbeckom@clcillinois.edu | (847)543-2631 |  | David | CBO
Sheridan | Shumsky | Grants Program Manager | College of Lake County | sshumsky@clcillinois.edu | (847) 543-2476 |  | David | Grant Manager
Rebecca | Bode |  | College of Lake County | rbode@clcillinois.edu |  |  | David | Facility Mngr
Mahsa | Karamy | Executive Director of Facilities and Auxiliary Services | College of Lake County | mkaramy@clcillinois.edu | (847) 543-2424 |  | David | Facility Mngr
Sari | Smart | Sustainability Manager | College of Lake County | ssmart1@clcillinois.edu | (847)453-2867 |  | David | Liaison | Sustainability Specialist | X
Jennifer | Evans |  | Lewis and Clark Community College | jnevans@lc.edu | (618) 468-3317 |  | Tim | Accounting
Carrie | Patton | Fiscal Grant Manager | Lewis and Clark Community College | cnpatton@lc.edu | (618) 468-3315 |  | Tim | Liaison
Christina | Russell | Manager of Auxiliary Services and Grants | Lewis and Clark Community College | ckrussell@lc.edu | (618) 468-2700 |  | Tim
Mary | Schulte | Vice President, Finance | Lewis and Clark Community College | mschulte@lc.edu |  |  | Tim | CBO
Keith | McLaughlin | President | Morton College | keith.mclaughlin@morton.edu | (708) 656-8000 ext. 2277 |  | Brad
Mireya | Perez | Chief Financial Officer/Treasurer | Morton College | Mireya.perez@morton.edu | (708) 656-8000 ext. 2289 |  | Brad | CBO
Brad | Sleeth | Faculty, Physical Science | Morton College | bradley.sleeth@morton.edu | (708) 656-8000 ext. 1316 |  | Brad | Liaison | Faculty Member | X
Chris | Clark | Vice President of Administrative Services | Shawnee Community College | chrisc@shawneecc.edu | (618) 634-3233 |  | Brad | Liaison | CBO | X
Tina | Dudley | Director of Facilities | Shawnee Community College | tinad@shawneecc.edu | (618) 634-3289 |  | Brad | Grant Manager
Christina | Wright | Accountant | Shawnee Community College | christinaw@shawneecc.edu |  |  | Brad | Grant Manager |  | X
Mike | Mance | Manager of Work Control | Southwestern Illinois College | michael.mance@swic.edu | 6189250409 |  | Tim
Brad | Sparks | Dean of Technical Education | Southwestern Illinois College | bradley.sparks@swic.edu | (618) 235-2700 ext. 5447 |  | Tim
Mike | Thomas | Director of Purchasing | Southwestern Illinois College | michael.thomas@swic.edu | (618) 222-5384 |  | Tim
Linda | Wegrzyn | Grants Manager | Southwestern Illinois College | linda.wegrzyn@swic.edu | (618) 641-5166 |  | Tim
Jacob | Wheeler | Chief Financial Officer | Southwestern Illinois College | jacob.wheeler@swic.edu | (618) 235-2700 ext. 6739 |  | Tim | CBO
Letitia | Slack | Purchasing Assistant | Southwestern Illinois College | letitia.slack@swic.edu |  |  | Tim | Liaison | Accounting | x
5
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liaison has to be in the “Primary Role” position.